## WBS Cost Spreadsheet
Time-Cost Labor Estimates
WBS ID | Task Description | Task Assigned to | Estimate (hrs) | Estimating Approach | Estimate (hrs) | Estimated Interruptions (hrs) ( Estimate * 0.33) | Total Effort (hrs) | Labor Rate $/hr | Labor Cost Total $ | Expenses | Total Costs | # of Resources | Calendar duration
1.0 | Project FPD DM Dashboard
1.1 | Define Requirements
1.1.1 | Conduct QlikSense AI tool Training (Don't factor the hours - Assume full time training for this only) | Dean, Jess, Paris | 40 | Expert | 120 | 0 |  |  | 0 | 10000 | 10000 | 3 | 0
1.1.2-4 | Requirements | William, Taraji, Nia | 80 | Expert/Bottom-Up | 24 | 26.4 | 50.4 | 120 | 6048 | 0 | 6048 | 3 | 16.8
1.2 | Design Dashboard
1.2.1 | Conceptual Design - Defining Entities Relationships | William, Taraji, | 40 | Bottom Up Estimating | 40 | 13.2 | 53.2 | 40 | 2128 |  | 2128 | 3 | 26.6
1.2.2 | Create ERD | Nia, Samuel | 40 | Parametic Estimating | 40 | 13.2 | 53.2 | 40 | 2128 |  | 2128 | 2 | 13.3
1.2.2 | Logical Design | William, Taraji, | 40 | Parametic Estimating | 40 | 13.2 | 53.2 | 40 | 2128 |  | 2128 | 3 | 26.6
1.2.3 | Physical Design | William, Taraji, Nia | 40 | Bottom Up Estimating | 40 | 13.2 | 53.2 | 120 | 6384 |  | 6384 | 6 | 13.3
1.3 | Source/Cleanse data
1.3.2 | Data Mapping | Nia | 10 | Vendor Bid Analysis | 10 | 3.3 | 13.3 | 40 | 532 |  | 532 | 2 | 6.65
1.3.3 | Data Extracting/Pre-processing Protocol | Nia | 15 | Bottom Up Estimating | 15 | 4.95 | 19.95 | 40 | 798 |  | 798 | 2 | 9.975
1.3.4 | Data Cleaning | Nia | 10 | Bottom Up Estimating | 10 | 3.3 | 13.3 | 40 | 532 |  | 532 | 2 | 6.65
1.3.5 | Validate Data Migration | Nia | 5 | Expert | 5 | 1.65 | 6.65 | 40 | 266 |  | 266 | 2 | 3.325
1.4 | Develop analytics models
1.4.1 | Database Set Up/Frame Work | Analyst Team | 120 | Parametic Estimating | 100 | 33 | 133 | 160 | 21280 |  | 21280 | 2 | 66.5
1.4.2 | Install Database Server | Analyst Team | 40 | Expert | 40 | 13.2 | 53.2 | 160 | 8512 |  | 8512 | 2 | 26.6
1.4.3 | Implement Schema | Analyst Team | 40 | Bottom Up Estimating | 40 | 13.2 | 53.2 | 160 | 8512 |  | 8512 | 2 | 26.6
1.5 | Construct/Modify dashboard
1.5.1 | Load Initital Data | Samuel Lincoln | 40 | Three Point Estimating | 140 | 46.2 | 186.2 | 80 | 14896 |  | 14896 | 2 | 93.1
1.5.2 | Perforam Data Validation | William, Taraji, | 120 | Bottom Up Estimating | 120 | 39.6 | 159.6 | 160 | 25536 |  | 25536 | 1 | 159.6
1.5.3 | Optimize Data Loading | William, Taraji, | 40 | Bottom Up Estimating | 40 | 13.2 | 53.2 | 160 | 8512 |  | 8512 | 1 | 53.2
1.6 | Test Dashboard
1.6.1 | Test Plan(s) | William | 100 | Expert Judgement | 100 | 33 | 133 | 40 | 5320 |  | 5320 | 1 | 133
1.6.2 | Performance Testing | William | 100 | Three Point Estimating | 100 | 33 | 133 | 40 | 5320 |  | 5320 | 1 | 133
1.6.3 | Security Testing | William | 40 | Expert Judgement | 40 | 13.2 | 53.2 | 40 | 2128 |  | 2128 | 1 | 53.2
1.7 | Train Users
1.7.1 | User Guide | Jamie Wolf | 25 | Parametic Estimating | 25 | 8.25 | 33.25 | 40 | 1330 |  | 1330 | 1 | 33.25
1.7.2 | Technical Guide | Jamie Wolf | 25 | Bottom Up Estimating | 25 | 8.25 | 33.25 | 40 | 1330 |  | 1330 | 1 | 33.25
1.7.3 | IT Training | Jamie Wolf | 20 | Expert | 20 | 6.6 | 26.6 | 40 | 1064 |  | 1064 | 1 | 26.6
1.7.4 | Makreting and Sales Training | Jamie Wolf | 10 | Expert | 10 | 3.3 | 13.3 | 40 | 532 |  | 532 | 1 | 13.3
1.8 | Deploy Dashboard
1.8.1 | Deployment Plan | William | 20 | Expert Judgement | 20 | 6.6 | 26.6 | 40 | 1064 |  | 1064 | 1 | 26.6
1.8.2 | Production Environment | Taraji | 20 | Bottom Up Estimating | 20 | 6.6 | 26.6 | 40 | 1064 |  | 1064 | 1 | 26.6
1.8.3 | Final Data Migration | Nia | 20 | Three Point Estimating | 20 | 6.6 | 26.6 | 40 | 1064 |  | 1064 | 1 | 26.6
1.8.4 | Final Testing, Go Live | William | 20 | Expert Judgement | 20 | 6.6 | 26.6 | 40 | 1064 |  | 1064 | 1 | 26.6
1.9 | Project Management (Put all project management time here - assume full time or half time and don't factor)
1.9.1 | Project Plan | Project Manager | 20 | Expert Judgement | 20 | 6.6 | 26.6 | 55 | 1463 |  | 1463 | 1 | 26.6
1.9.2 | Project Exexcution | Project Manager | 40 | Three Point Estimating | 40 | 13.2 | 53.2 | 55 | 2926 |  | 2926 | 1 | 53.2
1.9.3 | Project Monitoring | Project Manager | 60 | Three Point Estimating | 940 | 19.8 | 959.8 | 55 | 52789 |  | 52789 | 1 | 959.8
1.9.4 | Final Reports | Project Manager | 20 | Analagous Estimating | 20 | 6.6 | 26.6 | 55 | 1463 |  | 1463 | 1 | 26.6
[9 empty] | 188113 | 0 | 198113 | 61
| Total | [7 empty] | 0 | 0 | 0
396226