## Sheet1
Work Breakdown Structure Dictionary
Project Name:
FPD Drinking Metrics
Project Manager:
Jamia Russell
Organization:
FDP Beverage Company
Date:
2024-07-01
| WBS Number | Deliverable | Task Owner | Description
| 1.1 | Define Requirements
| 1.1.1 | Functional Requirements Document | William Jones (Database Analys I)
| 1.1.2 | Gather Non-Functional Requirements | Taraji Samson (Database Analyst II)
| 1.1.3 | Document Requirements | Williams Jones (Database Anakyst I)
| 1.3.1 | Validate Requirements | Analyst Team
| 1.2 | Design Dashboard
| 1.2.1 | Conceptual Dashboard Design | Analyst Team
| 1.2.2 | ERD Diagram | Nia Short (ERP Analyst I)
| 1.2.3 | Logical Design | Taraji Samson (Database Analyst II)
| 1.2.4 | Physical Design | Analyst Team
| 1.3 | Source/Cleanse Data
| 1.3.1 | Data Sourcing Document | Nia Short (ERP Analyst I)
| 1.3.2 | Data Mapping Document | Big Data Training Group Rep
| 1.3.3 | Data Extraction/Pre-processing Protocol | Samuel Lincoln (ERP Analyst II)
| 1.3.4 | Data Cleansing Report | Nia Short (ERP Analyst I)
| 1.3.5 | Data Migration Validation Report | Samuel Lincoln (ERP Analyst II)
| 1.4 | Develop Analytics Model
| 1.4.1 | Database Set Up Outline | W. Jones (Database Analyst I)
| 1.4.2 | Database Server Installation | T. Samson (Database Analyst II)
| 1.4.3 | Schema Implementation | W. Jones & T. Samson
| 1.5 | Construct Modify Dashboard
| 1.5.1 | Initial Data Loading | N. Short and W. Jones
| 1.5.2 | Data Validation Report | N. Short and S. Lincoln
| 1.5.3 | Data Optimization Report | T. Samson (Database Analyst II)
| 1.6 | Testing
| 1.6.1 | Test Plan(s) | Analyst Team
| 1.6.2 | System Testing Report | Analyst Team
| 1.6.3 | Performance Testing Report | W. Jones
| 1.6.4 | Security Testing Report | Analyst Team
| 1.7 | User Training
| 1.7.1 | User Guide | Jamie Wolf
| 1.7.2 | Technical Guide | Jamie Wolf
| 1.7.3 | IT Training | Jamie Wolf
| 1.7.4 | Marketing and Sales Teams Training | Jamie Wolf
| 1.8 | Deploy Dashboard
| 1.8.1 | Deployment Plan | William
| 1.8.2 | Production Envrionment | Taraji Samson (Database Analyst II)
| 1.8.3 | Final Data Migration Report | Nia Short (ERP Analyst I)
| 1.8.4 | Final Testing Report | Analyst Team
| 1.9 | Project Management
| 1.9.1 | Project Plan | Project Manager
| 1.9.2 | Project Execution | Project Manager
| 1.9.3 | Project Monitoring and Control | Project Manager
| 1.9.4 | Project Close | Project Manager
The method chosen for the WBS is the top down approach each bolden encoding represents the largest deliverable/project outcome and are
broken down into smaller deliverables/work packages that will complete the larger task. Each task owner has specific knowledge that w
ill aid in completing the work package efficiently. The choice of the topdown approach compared to the bottom up, or hybrid approach to complete this
project is clear due to the need of a clear deliverable in mind that each smaller deliverable should aid in accomplishing. The bottom up approach would
not offer the clarity of the expected goals as they align with the project timeline.