## FPDD Gantt Chart 02
|  | FPD DM Gantt Chart | [7 empty] | Time Period ( 10 work-day periods)
[5 empty] | 10 | 20 | 30 | 40 | 50 | 60 | 70 | 80 | 90 | 100 | 110 | 120 | 130
[5 empty] | Month 1 |  | Month 2 |  | Month 3 |  | Month 4 |  | Month 5 |  | Month 6
Activity | Duration | ES | LF | Slack | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26
A. Define Requirements | 10 | 0 | 10 | 0 | bar: 2
B. Design Dashboard | 20 | 10 | 30 | 0 | bar: 4 to 6
C. Source/Cleanse Data | 5 | 10 | 30 | 15 | bar: 4 to 6
D. Develop Analytics Model | 25 | 30 | 55 | 0 | bar: 8 to 10
E. Construct DB Software | 25 | 55 | 80 | 0 | bar: 14 to 16
F. Test Software | 30 | 80 | 110 | 0 | bar: 18 to 22
G. Train Users | 10 | 110 | 120 | 0 | bar: 24
H. Deploy DB | 10 | 120 | 130 | 0 | bar: 26
I. Project Management | 130 | 0 | 130 | 0
Critical Path: ABDEFGH
Duration: 130 days |  |  |  |  | 22: EOC Review
Define Requirements
[5 empty] | 8: Dashboard Design; 18: Analytics Model and; 24: Deployment | Project Closed
Dashbaord Complete
SLACK

## Copy of FPDD Gantt Chart 02
|  |  | FPD DM Gantt Chart | [8 empty] | Time Period ( 2 week periods)
|  |  | (status 8/31) |  |  |  | 80 | 160 | 240 | 320 | 400 | 480 | 560 | 640 | 720 | 800 | 880 | 960 | 1040
[7 empty] | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec
Budget | Activity | Duration | ES | LF | Slack | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26
8000 | A. Define Requirements | 80 | 0 | 80 | 0
16000 | B. Design Dashboard | 160 | 80 | 240 | 0
2000 | C. Acquire Hardware/Software | 40 | 80 | 160 | 80 |  |  |  | SLACK
104000 | D. Construct DB Software | 400 | 240 | 640 | 0
24000 | E. Test Software | 240 | 640 | 880 | 0
6000 | F. Train Users | 80 | 880 | 960 | 0
2000 | G. Deploy DB | 80 | 960 | 1040 | 0
67600 | H. Project Management | 1040 | 0 | 1040 | 0
229600
[10 empty] | Prototype done | [6 empty] | EOC Review |  | FPPD deployed

## Revised Budget
Budget | Activity
|  |  |  | FPD DM Gantt Chart | [10 empty] | Time Period ( 2 week periods - with some broken down into smaller increments)
8000 | A. Define Requirements
16000 | B. Design Dashboard | [9 empty] | 80 | 160 | 240 | 320 | 400 | 480 | 560 | 640 |  | 720 |  | 800 | 880 | 960 | 1040
2000 | C. Acquire Hardware/Software | [9 empty] | Jul |  | Aug |  | Sep |  | Oct |  |  | Nov |  |  | Dec
104000 | D. Construct DB Software | Budget | Activity | Duration | ES | EF | LS | LF | Slack | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 |  | 18 |  | 20 | 22 | 24 | 26
6000 | E. Additional Data per Change Request
51000 | F. Test Software | 8000 | A. Define Requirements | 80 | 0 | 80 | 0 | 80 | 0
6000 | G. Train Users | 16000 | B. Design Dashboard | 160 | 80 | 240 | 80 | 240 | 0
1000 | H. Deploy DB | 2000 | C. Acquire Hardware/Software | 40 | 80 | 120 | 160 | 200 | 80 |  |  |  | SLACK
50700 | I. Project Management | 104000 | D. Construct DB Software | 240 | 240 | 480 | 240 | 480 | 0
5300 | Emergency (Add'l. Expenses, Consulting, etc.) | 6000 | E. Additional Data per Change Request | 240 | 320 | 560 | 420 | 660 | 100 | [8 empty] | SLACK
250000 |  | 51000 | F. Test Software | 180 | 480 | 660 | 480 | 660 | 0
|  | 6000 | G. Train Users | 80 | 660 | 740 | 660 | 740 | 0
|  | 1000 | H. Deploy DB | 40 | 740 | 780 | 740 | 780 | 0
|  | 50700 | I. Project Management | 780 | 0 | 780 | 0 | 780 | 0
244700
[14 empty] | Prototype Done |  |  |  |  | EOC Review |  | FPDD Deployed |  | Software Freeze | Holiday Shutdown